## Matrix
Task Group | Function Code | Task | Comlexity Points | Estimated Duration (hours) | Number Of Bugs | Note
Design Discussion | DEG_01 | Discuss issue that only ralates to business logic | 1 | 1
| DEG_02 | Discuss issue that relates to business logic, cache and database | 2 | 2
| DEG_03 | Discuss issue that relates to core | 3 | 3
| DEG_04 | Discuss issue that relates to external system | 4 | 4
Develop API | API_01 | Develop API that only ralates to business logic and call other APIs | 1 | 3
| API_02 | Develop API that relates to manipulate cache | 2 | 6
| API_03 | Develop API that relates to manipulate database | 3 | 9
| API_04 | Develop API that relates to manipulate cache and database | 4 | 12
Bug Produce | BUG_01 | Bug produce while developing front-end feature in 1 hour | 1 |  | 0.125
| BUG_02 | Bug produce while developing back-end feature in 1 hour | 2 |  | 0.25
Bug Fix | FIX_01 | Fix simple bug front-end | 1 | 1
| FIX_02 | Fix medium bug front-end | 2 | 2
| FIX_03 | Fix complex bug front-end | 3 | 3
| FIX_04 | Fix simple bug back-end | 2 | 2
| FIX_05 | Fix medium bug back-end | 3 | 3
| FIX_06 | Fix complex bug back-end | 4 | 4
Join Meeting | MEE_01 | Join retrospective meeting | 1 | 1
| MEE_02 | Join grooming meeting | 2 | 2
Manual Test | MAN_01 | Test simple feature manually | 1 | 4
| MAN_02 | Test medium feature manually | 2 | 8
| MAN_03 | Test complex feature manually | 3 | 16
Automation Test | AUT_01 | Develop script to test simple API | 1 | 1
| AUT_02 | Develop script to test medium API | 2 | 2
| AUT_03 | Develop script to test complex API | 3 | 3

## Estimation
Task | Sub Task | Function Code | Estimated Duration (hours) | Estimated Introduced Bug
|  | DEG_03 | 3